## Time sheet
[5 empty] | Legenda: |  |  |  |  | = weekend days | [6 empty] | = Legal Holiday | [6 empty] | = Planned Holiday
| year |  | TOTAL spent hours | 13 | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D
| 2018 |  | Project: CATALOG SCOLAR CLASELE 9 - 12 | hours | time axis 2018-04-26 to 2018-12-03
1. | General issues | 1.1 | GitHub - tutorials / understanding | 3 | 2018-04-26: 3
|  | 1.2 | GitHub - create account / settings / understand functionality | 4 | 2018-04-27: 1; 2018-04-28: 3
|  | 1.3 | Kick-of discussion / define the strategy with Project Leader | 1 | bar: 2018-04-26
|  | 1.4 | Design wireframe and general functionality / purpose | 1 | bar: 2018-04-28
|  | 1.5 | Update the files on GitHub | 0
|  | 1.6 | Communicate / feedback / status / define next changes / steps | 0
|  | 1.7 | Create MVC structure | 2 | 2018-04-27: 2
|  | 1.8 | Develop MVC structure | 0
|  | 1.9 | Working on project time-sheet | 2 | 2018-04-28: 2
|  |  | (if needed insert new line) | 0
2. | Welcome page | 2.1 | Header with 3 nav. Buttons: Home / Login /Sign up | 0
|  | 2.2 | Create main / home page - not logged in | 0
|  | 2.3 | Design Footer - include: contact us / links to FB / TW / … | 0
|  | 2.4 | Add 1 new button in header - About us | 0
|  | 2.5 |  | 0
|  | 2.6 |  | 0
|  | 2.7 |  | 0
|  | 2.8 |  | 0
|  | 2.9 |  | 0
|  |  | (if needed insert new line) | 0
3. | Login system | 3.1 | Design the log-in form | 0
|  | 3.2 | Log-in form validation - empty fields / user-mail / special char. | 0
|  | 3.3 | Log-in form validation - existing records in DB - user / pw | 0
|  | 3.4 | Protect pw after form validation - record in DB | 0
|  | 3.5 | Design sing up form - student | 0
|  | 3.6 | Design sing up form - parent | 0
|  | 3.7 | Design sing up form - professor | 0
|  | 3.8 | design | 0
|  | 3.9 |  | 0
|  |  | (if needed insert new line) | 0
4. | Logged in pages | 4.1 | Header logged in: button "logout" instead of "login" | 0
|  | 4.2 | Customized header / professor user: record notes feature | 0
|  | 4.3 | Add in header: show notes - button for all users | 0
|  | 4.4 | Assure functionality for DB interogations | 0
|  | 4.5 | Show info about user after log-in: name / lastname / | 0
|  | 4.6 | Add in header: show absences - button for all users | 0
|  | 4.7 | Prof. page: insert button to record individual notes | 0
|  | 4.8 | Prof. page: add drop-down menu for fields - Clasa, Semestru, nota | 0
|  | 4.9 |  | 0
|  | 4.1 |  | 0
|  |  | (if needed insert new line) | 0
5. | Database | 5.1 | Create DB + user table / admin / student / parent / professor | 0
|  | 5.2 | Create tabel - topyc of study | 0
|  | 5.3 | Create tabel - notes | 0
|  | 5.4 | Create tabel - absences | 0
|  | 5.5 | Create tabel - students | 0
|  | 5.6 | Create tabel - parents | 0
|  | 5.7 | Create tabel - professors | 0
|  | 5.8 |  | 0
|  | 5.9 |  | 0
|  |  | (if needed insert new line) | 0
6. | Front end & Jscript | 6.1 | Define behaviour for Welcome page | 0
|  | 6.2 | Learning JavaScript | 0
|  | 6.3 |  | 0
|  | 6.4 |  | 0
|  | 6.5 |  | 0
|  | 6.6 |  | 0
|  | 6.7 |  | 0
|  | 6.8 |  | 0
|  | 6.9 |  | 0
|  |  | (if needed insert new line) | 0
7. | Tests & Deployment | 7.1 | Test the application - IE | 0
|  | 7.2 | Test the application - Chrome | 0
|  | 7.3 | Test the application - Mozilla Firefox | 0
|  | 7.4 | Test the application - Opera | 0
|  | 7.5 | Test the application - windows 7 / windows 10 / MAC | 0
|  | 7.6 |  | 0
|  | 7.7 |  | 0
|  | 7.8 |  | 0
|  | 7.9 |  | 0
|  |  | (if needed insert new line) | 0
8. | Other | 7.1 |  | 0
|  | 7.2 |  | 0
|  | 7.3 |  | 0
|  | 7.4 |  | 0
|  | 7.5 |  | 0
|  | 7.6 |  | 0
|  | 7.7 |  | 0
|  | 7.8 |  | 0
|  | 7.9 |  | 0
|  |  | (if needed insert new line) | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0